## Sheet1
Test case and execution status tracking
Project: Uniform Store
slno | module | Test case written and reviewed | Date | Estimated effort | Actual Effort | Reason for variance(if any)
1 | Customer addition | 4 | 2021-04-08 | 30m | 45m | N/A
2 | Empty Customer | 5 | 2021-04-05 | 30m | 40m | N/A
3 | Customer Updation | 4 | 2021-04-05 | 30m | 30m | N/A
4 | Customer Deletion | 3 | 2021-04-05 | 20m | 25m | N/A
5 | Customer Search | 1 | 2021-04-05 | 15m | 15m | N/A